## Final Schedule
|  |  | Final schedule for run 1 rob | [5 empty] | Table
|  |  | PLANTING | INNOCULATION | END INNOCULATION | ADD BIOTYPES | COUNT APHIDS
2018-09-01 | 1 | Saturday | Plant Alfalfa and Red Clover |  |  |  |  | Species | Germination (days) | Infect duration | PEMV buildup | Biotypes duration | TOTAL TIME
2018-09-02 | 2 | Sunday | [5 empty] | Red Clover | 28 | 3 | 7 | 7 | 45
2018-09-03 | 3 | Monday | [5 empty] | Alfalfa | 22 | 3 | 7 | 7 | 39
2018-09-04 | 4 | Tuesday | [5 empty] | Hairy Vetch | 21 | 3 | 7 | 7 | 38
2018-09-05 | 5 | Wednesday | [5 empty] | Faba | 13 | 3 | 7 | 7 | 30
2018-09-06 | 6 | Thursday | Plant Hairy Vetch |  |  |  |  | Pea | 10 | 3 | 7 | 7 | 27
2018-09-07 | 7 | Friday | [5 empty] | Lentil | 10 | 3 | 7 | 7 | 27
2018-09-08 | 8 | Saturday
2018-09-09 | 9 | Sunday
2018-09-10 | 10 | Monday
2018-09-11 | 11 | Tuesday
2018-09-12 | 12 | Wednesday | Plant Lentil, Pea, and Fava
2018-09-13 | 13 | Thursday
2018-09-14 | 14 | Friday
2018-09-15 | 15 | Saturday
2018-09-16 | 16 | Sunday
2018-09-17 | 17 | Monday
2018-09-18 | 18 | Tuesday
2018-09-19 | 19 | Wednesday
2018-09-20 | 20 | Thursday
2018-09-21 | 21 | Friday
2018-09-22 | 22 | Saturday |  | Add infective aphids to Pea, Lentil
2018-09-23 | 23 | Sunday |  | Add infective aphids to Alfalfa
2018-09-24 | 24 | Monday
2018-09-25 | 25 | Tuesday |  | Add infective aphids to Fava | Remove infective aphids from Pea and Lentil
2018-09-26 | 26 | Wednesday |  |  | Remove infective aphids from Alfalfa
2018-09-27 | 27 | Thursday |  | Add infective aphids to Vetch
2018-09-28 | 28 | Friday |  |  | Remove Innoculated aphids from Fava
2018-09-29 | 29 | Saturday |  | Add infective Aphdis to Clover
2018-09-30 | 30 | Sunday |  |  | Remove Innoculated Aphids from Vetch
2018-10-01 | 31 | Monday
2018-10-02 | 32 | Tuesday |  |  | Remove Innoculated Aphids from Clover | Put biotypes on Pea and Lentil
2018-10-03 | 33 | Wednesday |  |  |  | Put biotypes on Alfalfa
2018-10-04 | 34 | Thursday
2018-10-05 | 35 | Friday |  |  |  | Put biotypes on Fava
2018-10-06 | 36 | Saturday
2018-10-07 | 37 | Sunday |  |  |  | Put biotypes on Vetch
2018-10-08 | 38 | Monday
2018-10-09 | 39 | Tuesday |  |  |  | Put biotypes on Clover | Count aphids on Pea and Lentil
2018-10-10 | 40 | Wednesday |  |  |  |  | Count ahpids on Alfalfa
2018-10-11 | 41 | Thursday
2018-10-12 | 42 | Friday |  |  |  |  | Count Aphids on Fava
2018-10-13 | 43 | Saturday
2018-10-14 | 44 | Sunday |  |  |  |  | Count Aphids on Vetch
2018-10-15 | 45 | Monday
2018-10-16 | 46 | Tuesday |  |  |  |  | Count Aphids on Clover
2018-10-17 | 47 | Wednesday
2018-10-18 | 48 | Thursday
2018-10-19 | 49 | Friday
2018-10-20 | 50 | Saturday
2018-10-21 | 51 | Sunday

## Calcls
Duration | Timing | Event | Duration | Rob day of week | Rob timing | Event |  |  |  | Final schedule for run 1 rob
1 | 2018-02-01 | Alfalfa, Red Clover and Vetch Planted | 1 | Saturday | 2018-09-01 | Alfalfa, Red Clover and Vetch Planted (old vetch date) | 2018-09-01 | 1 | Saturday | Plant Alfalfa and Red Clover
2 | 2018-02-02 |  | 2 | Sunday | 2018-09-02 |  | 2018-09-02 | 2 | Sunday
3 | 2018-02-03 |  | 3 | Monday | 2018-09-03 |  | 2018-09-03 | 3 | Monday
4 | 2018-02-04 |  | 4 | Tuesday | 2018-09-04 |  | 2018-09-04 | 4 | Tuesday
5 | 2018-02-05 |  | 5 | Wednesday | 2018-09-05 |  | 2018-09-05 | 5 | Wednesday
6 | 2018-02-06 |  | 6 | Thursday | 2018-09-06 | new plant vetch date | 2018-09-06 | 6 | Thursday | Plant Hairy Vetch
7 | 2018-02-07 |  | 7 | Friday | 2018-09-07 |  | 2018-09-07 | 7 | Friday
8 | 2018-02-08 |  | 8 | Saturday | 2018-09-08 |  | 2018-09-08 | 8 | Saturday
9 | 2018-02-09 | Lentil, Pea, and Fava Planted | 9 | Sunday | 2018-09-09 | Lentil, Pea, and Fava Planted (old date -ignore ) | 2018-09-09 | 9 | Sunday
10 | 2018-02-10 |  | 10 | Monday | 2018-09-10 |  | 2018-09-10 | 10 | Monday
11 | 2018-02-11 |  | 11 | Tuesday | 2018-09-11 |  | 2018-09-11 | 11 | Tuesday
12 | 2018-02-12 |  | 12 | Wednesday | 2018-09-12 | Lentil, Pea, and Fava Planted (new date) | 2018-09-12 | 12 | Wednesday | Plant Lentil, Pea, and Fava
13 | 2018-02-13 |  | 13 | Thursday | 2018-09-13 |  | 2018-09-13 | 13 | Thursday
14 | 2018-02-14 |  | 14 | Friday | 2018-09-14 |  | 2018-09-14 | 14 | Friday
15 | 2018-02-15 |  | 15 | Saturday | 2018-09-15 |  | 2018-09-15 | 15 | Saturday
16 | 2018-02-16 |  | 16 | Sunday | 2018-09-16 |  | 2018-09-16 | 16 | Sunday
17 | 2018-02-17 |  | 17 | Monday | 2018-09-17 |  | 2018-09-17 | 17 | Monday
18 | 2018-02-18 |  | 18 | Tuesday | 2018-09-18 |  | 2018-09-18 | 18 | Tuesday
19 | 2018-02-19 | Innoculate Pea, Lentil | 19 | Wednesday | 2018-09-19 | Innoculate Pea, Lentil (old date - ignore) | 2018-09-19 | 19 | Wednesday
20 | 2018-02-20 |  | 20 | Thursday | 2018-09-20 |  | 2018-09-20 | 20 | Thursday
21 | 2018-02-21 |  | 21 | Friday | 2018-09-21 |  | 2018-09-21 | 21 | Friday
22 | 2018-02-22 | Innoculate fava | 22 | Saturday | 2018-09-22 | Innoculate fava, new innoculate pea and lentil | 2018-09-22 | 22 | Saturday | Add infective aphids to Pea, Lentil
23 | 2018-02-23 | innoculate vetch and alfalfa that are large enough | 23 | Sunday | 2018-09-23 | innoculate vetch that are large enough (old innoculate date) | 2018-09-23 | 23 | Sunday | Add infective aphids to Alfalfa
24 | 2018-02-24 |  | 24 | Monday | 2018-09-24 |  | 2018-09-24 | 24 | Monday
25 | 2018-02-25 |  | 25 | Tuesday | 2018-09-25 | new innoculate fava date | 2018-09-25 | 25 | Tuesday | Add infective aphids to Fava | Remove infective aphids from Pea and Lentil
26 | 2018-02-26 |  | 26 | Wednesday | 2018-09-26 |  | 2018-09-26 | 26 | Wednesday |  | Remove infective aphids from Alfalfa
27 | 2018-02-27 |  | 27 | Thursday | 2018-09-27 | new innoculate vetch date | 2018-09-27 | 27 | Thursday | Add infective aphids to Vetch
28 | 2018-02-28 |  | 28 | Friday | 2018-09-28 |  | 2018-09-28 | 28 | Friday |  | Remove Innoculated aphids from Fava
29 | 2018-03-01 | red clover innoculated | 29 | Saturday | 2018-09-29 | red clover innoculated, small vetch | 2018-09-29 | 29 | Saturday | Add infective Aphdis to Clover
30 | 2018-03-02 |  | 30 | Sunday | 2018-09-30 | Rob @ workshop in Scotland | 2018-09-30 | 30 | Sunday |  | Remove Innoculated Aphids from Vetch
31 | 2018-03-03 |  | 31 | Monday | 2018-10-01 | Rob @ workshop in Scotland | 2018-10-01 | 31 | Monday
32 | 2018-03-04 |  | 32 | Tuesday | 2018-10-02 | Rob @ workshop in Scotland | 2018-10-02 | 32 | Tuesday |  | Remove Innoculated Aphids from Clover | Put biotypes on Pea and Lentil
| 2018-03-05 |  | 33 | Wednesday | 2018-10-03 | Rob @ workshop in Scotland | 2018-10-03 | 33 | Wednesday |  |  | Put biotypes on Alfalfa
| 2018-03-06 |  | 34 | Thursday | 2018-10-04 | Rob @ workshop in Scotland | 2018-10-04 | 34 | Thursday
| 2018-03-07 |  | 35 | Friday | 2018-10-05 | Rob @ workshop in Scotland | 2018-10-05 | 35 | Friday |  |  | Put biotypes on Fava
| 2018-03-08 |  | 36 | Saturday | 2018-10-06 | Rob @ workshop in Scotland | 2018-10-06 | 36 | Saturday
| 2018-03-09 |  | 37 | Sunday | 2018-10-07 | Rob @ workshop in Scotland | 2018-10-07 | 37 | Sunday |  |  | Put biotypes on Vetch
| 2018-03-10 |  | 38 | Monday | 2018-10-08 | Rob @ workshop in Scotland | 2018-10-08 | 38 | Monday
| 2018-03-11 |  | 39 | Tuesday | 2018-10-09 | Rob @ workshop in Scotland | 2018-10-09 | 39 | Tuesday |  |  | Put biotypes on Clover | Count aphids on Pea and Lentil
| 2018-03-12 |  | 40 | Wednesday | 2018-10-10 |  | 2018-10-10 | 40 | Wednesday |  |  |  | Count ahpids on Alfalfa
| 2018-03-13 |  | 41 | Thursday | 2018-10-11 |  | 2018-10-11 | 41 | Thursday
| 2018-03-14 |  | 42 | Friday | 2018-10-12 |  | 2018-10-12 | 42 | Friday |  |  |  | Count Aphids on Fava
[7 empty] | 2018-10-13 | 43 | Saturday
[7 empty] | 2018-10-14 | 44 | Sunday |  |  |  | Count Aphids on Vetch
[7 empty] | 2018-10-15 | 45 | Monday
[7 empty] | 2018-10-16 | 46 | Tuesday |  |  |  | Count Aphids on Clover
[7 empty] | 2018-10-17 | 47 | Wednesday
[7 empty] | 2018-10-18 | 48 | Thursday
[7 empty] | 2018-10-19 | 49 | Friday
[7 empty] | 2018-10-20 | 50 | Saturday
[7 empty] | C | 51 | Sunday